# OAC Meeting Agenda Template

### EVERGREEN HEIGHTS COMPLEX

This template for the agenda of a pre-construction meeting is provided by Cogram. To automatically draft minutes in your template for in-person (e.g. site-visit or conference room) and online meetings, schedule a live demo.

### Overview

| Project Address Evergreen Heights Complex 1450 Maplewood Lane Crestview CA 92745 USA | Meeting Time 24.07.2024, 16:00 ET |  |
| --- | --- | --- |
|  | Project Number 012-345-67 |  |
|  | Purpose of Meeting OAC Meeting |  |
| Location of Meeting Virtual | Agenda created by Jane Smith, Architect (Ethereal Architects) |  |

### Attendees

| Name | Title & Role | Company | Email | Phone |
| --- | --- | --- | --- | --- |
| Jane Smith | Project Manager | Ethereal Architects | jsmith@etherealarch.com | (555) 123-4567 |
| John Doe | Client | Acme Corp | jdoe@acmecorp.com | (555) 876-5432 |

### Agenda Items

#### Critical Path Schedule Review

  - Current status

    - Discuss CP and all activities within 15 days of CP

    - Review 4-week rolling schedule and long lead items

  - Schedule

    - Discuss schedule changes: contract time extension requests, re-ordering, resequencing, and changing activity durations

  - Resource Allocation

    - Review resource allocation on critical path activities

    - Discuss float on near-critical activities

#### Constraint Log – All items potentially impacting the Critical Path

  - Discuss open constraints affecting critical path activities

  - Prioritize constraints based on urgency and impact

  - Review resource needs for critical constraints

  - Discuss strategies to prevent future constraints

#### Coordination Log

  - Open Requests for Information (RFIs)

    - Discuss top 5-10 critical RFIs

    - Evaluate schedule impacts of delayed responses

  - Submittal Status

    - Review the hot submittal list and critical items

    - Discuss overdue submittals and their impact

  - Design Changes or Updates

    - Review proposed design changes and rationale

    - Discuss budget, schedule, and quality implications

#### Project Schedule

  - Provide a high-level overview of the current status

  - Review 4-week look-ahead schedule

  - Discuss upcoming activities and milestones

  - Review deviations from the master schedule and contingency plans

#### Budget Review

  - Review the current project budget status

  - Discuss significant variances or potential cost overrun

  - Evaluate financial implications of pending change orders

#### Procurement and Material Status

  - Review long-lead items and critical materials status

  - Discuss potential supply chain issues or delivery delays

  - Review material substitution requests or approvals needed

#### Permitting and Regulatory Compliance

  - Review the status of required permits and inspections

  - Discuss upcoming regulatory requirements or deadlines

  - Review any compliance issues or concerns

#### Safety and Site Logistics

  - Review weekly toolbox topics

  - Discuss housekeeping, barricades, and area signage

  - Review site notices

  - Discuss any safety concerns or incidents since the last meeting

#### Quality Assurance / Inspections

  - Review completed QA/QC inspection results and non-conformances

  - Discuss upcoming inspections and testing requirements

  - Review final inspections and certificate of occupancy requirements

  - Discuss punch list items and Site Observation Reports (SOR)

#### Commissioning

  - Review the status of commissioning activities and schedule

  - Discuss commissioning issues impacting project completion

#### Stakeholder Questions and Updates

Attachments:

Please review this agenda and advise the writer of any corrections within 2 business days.